## Milestones
CAB Scope of Work Milestones Update
Milestone (See Attachment B to Scope of Work) | Due Date
• Initial status of the engineering and design of the project • Initial list of agreements, permits or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in First Progress Report 10/15/2024
• Status of the engineering and design of the project • List of agreements, permits or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in Second Progress Report 1/15/2025
• Minimum of at least one Reimbursement Request has been submitted | Submitted within 6 months of Effective Date or no later than 1/31/2025
No Required Milestone | Third Progress Report 4/15/2025
• Evidence of the start of construction • Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in Fourth Progress Report (End of First Year) 7/15/2025
• Minimum of two cumulative Reimbursement Requests have been submitted | Submitted within 1 year of Effective Date or no later than 7/31/2025
No Required Milestone | Fifth Progress Report 10/15/2025
• Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment • Access is available to 10% of the locations with submission of location data in the format designated by the office | Reported In Sixth Progress Report 1/15/2026
• Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported In Seventh Progress Report 4/15/2026
No Required Milestone | Eighth Progress Report 7/15/2026
No Required Milestone | Ninth Progress Report 10/15/2026
• Completion of the Construction Period • Access is available to 100% of the locations with submission of location data in the format designated by the office • Beginning of Maintenance Period | Reported in End of Construction Period Final Report or No Later Than 10/31/2026
• All reimbursement requests have been submitted | Final submission within 30 days of End of Construction or No Later Than 10/31/2026
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Maintenance Y1 Annual Report 7/15/2027
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Maintenance Y2 Annual Report 7/18/2028
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Maintenance Y3 Annual Report (Final Report End of Contract Period) 7/31/2029