## Milestones
CAB Round 2 Scope of Work Milestones Update
Milestone (See Attachment B to Scope of Work) | Due Date
• Initial status of the engineering and design of the project • Initial list of agreements, permits or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in First Progress Report 7/15/2025
• Minimum of at least one Reimbursement Request has been submitted | Submitted within 6 months of Effective Date or no later than 10/1/2025
• Status of the engineering and design of the project • List of agreements, permits or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in Second Progress Report 10/15/2025
• Evidence of the start of construction • Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported in Third Progress Report 1/15/2026
• Minimum of two cumulative Reimbursement Requests have been submitted | Submitted within 1 year of Effective Date or no later than 4/1/2026
• Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Fourth Progress Report 4/15/2026
• Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment • Access is available to 10% of the locations with submission of location data in the format designated by the office | Reported In Fifth Progress Report 7/15/2026
• Status of the engineering and design of the project • List of agreements, permits, or contractual arrangements that must be acquired or executed to construct or deploy infrastructure/equipment | Reported In Sixth Progress Report 10/15/2026
• Completion of the Construction Period • Access is available to 100% of project locations • Beginning of Maintenance Period | No Later Than 10/31/2026
• All reimbursement requests have been submitted | Final submission within 30 days of End of Construction But No Later Than 10/31/2026
• Access is available to 100% of the locations with submission of location data in the format designated by the office | Reported in End of Construction Period Final Report due 30 days after completion of construction
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Y1 Annual Maintenance Report due
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Y2 Annual Maintenance Report
• Submittal of an attestation demonstrating compliance with Broadband Access and Speed requirements pursuant to this agreement | Reported in Y3 Annual Maintenance Report
The schedule above assumes a full nineteen-month construction period (April 1, 2025 through Oct. 31, 2026). The contractor may move from a quarterly to an annual reporting period prior to the date above if the construction period of the project is completed early.