## Slide 1
Office of Digital Opportunity
Grant Closeout Webinar
March 5, 2026

## Slide 2
Agenda
What is Closeout?
Key Dates/Closeout Process
  Completion of Programmatic Activities
  Submission of Final Program Report
  Final Funds Request
    Subrecipient Reconciliation
    Submission of Final Finance Reporting
  Notification of Grant Closeout
FAQs
Q&A

## Slide 3
What is Closeout?
It’s the process by which we confirm that all grant award administrative requirements and programmatic obligations have been completed, including submission of all required reports and reconciliation of cash balances, marking the official end of the grant award lifecycle.
Closeout may occur before or after the anticipated project end date, depending on the grantee specific timeline.

## Slide 4
Grant Closeout Phases and Key Dates
Phase 1: Final Fund Request | Sept. 1-4, 2026 | Grantees may request programmatic costs, estimated administrative and closeout costs, and applicable indirect costs.
Phase 2: End of Program Activities | Sept. 30, 2026 | All programmatic activities and the incurrence of new obligations must end by Sept. 30, 2026. This end date applies to both the grantee and any subrecipients. Program costs: Through Sept. 30 Closeout/admin costs: October-December
Phase 3: Subrecipient Reconciliation | Oct. 1-30, 2026 | This period allows for the primary grantee to receive final expenditure reports/documents from the subrecipient. Grantees should encourage their subrecipients to: Finalize documentation Close their books for the activity period Submit final reporting
Phase 4: Submission of Final Program Report | Nov. 20, 2026 | The final programmatic report will be completed via link by Nov. 20.
Phase 5: Submission of Final Finance Reporting | Jan. 8, 2027 | The final finance reporting is due by Jan. 8, 2027. Expenditure report Finance Certification Budget Reconciliation
Phase 6: Notification of Grant Closeout | Ongoing | Once all required documentation has been received, reviewed, and any unspent funds returned (if applicable), grantees will receive a formal closeout letter indicating that all programmatic and financial obligations have been fulfilled and the grant is officially closed.

## Slide 5
Programmatic activities funded by this grant should be completed by Sept. 30, 2026. This includes all deliverables outlined in your grant application, such as digital skills classes and device distribution.
  If you anticipate difficulty completing programmatic activities by this date, please contact your program/finance officers as soon as possible.
  Our team will support activities tied to existing documented commitments. No new programming may begin after Sept. 30.
Subrecipients’ programmatic activities must also be completed by Sept. 30, 2026.
  We encourage you to begin conversations with them now to ensure alignment. You have flexibility to manage subrecipient timelines based on capacity. If you determine that their activities should conclude prior to Sept. 30, you may do so.
Completion of Programmatic Activities​

## Slide 6
Submission of Final Program Report
Your final program report will be completed via a survey link.
What were the primary objectives of your program or project? Please include specific, measurable goals or outcomes where applicable.
Final Program totals: Devices distributed, digital skills trainings conducted, number of individuals served
Number of subrecipients/beneficiaries
Key accomplishments
Challenges
Lessons learned
Plans for sharing best practices
Success/impact stories
Feedback for the Office of Digital Opportunity
The story of your work: what you achieved, what was hard, and what you learned.
Prompts from Final Report

## Slide 7
Final Fund Request Window & Allowable Costs
Covers October-December
Although programmatic activities end Sept. 30, the September drawdown should include costs that will be incurred through December related to closeout.
Sept. 1-4 (Final Request Window)
Preparing final programmatic and financial reports​
Reconciling grant expenses​ (i.e., final contract/consultant costs)
Reviewing and closing out subrecipient costs (if applicable)​
Organizing records for retention​
Accounting or finance support related to closeout​
Audit costs ​
Finalize and report key performance indicators
Facility costs incurred during the closeout period for space used to complete required grant closeout activities ​
Storage costs incurred during closeout period to support required components such as record retention, or disposition of grant related materials. ​
Personnel costs necessary to complete required grant closeout activities:​
  Closeout processes: Gather/organize documentation to support compliance with policies, procedures, internal controls, federal and state requirements, proof of payment​.
  Gather/organize documentation to outline program successes, challenges and best practices for internal and external communication and to ensure future program sustainability.
Allowable Costs beyond Sept. 30 (Oct-Dec): ​

## Slide 8
Submitting Final Finance Closeout Documents
Final expenditure report reflecting all expenses incurred through Dec. 31
Budget reconciliation report
Inventory sheet of all equipment purchased with grant funds, regardless of cost
Closeout certification form
Most recent single audit report
Include the following items by Jan. 8, 2027
Grantees will meet with their finance officer to review any remaining balances prior to completing the finance closeout form.
Grantees will receive the closeout certification template and submit it with their final report.
Once the finance officer confirms the amount to be returned (if any), any undrawn funds or that all funds have been fully expended, the document will be routed for signature.
Finance Officer Support

## Slide 9
Notification of Grant Closeout & Record Retention
Once all required documentation has been received and reviewed, and any unspent funds have been returned (if applicable), grantees will receive a formal closeout letter confirming that all programmatic and financial obligations have been fulfilled and the grant is officially closed.
While the grant portal is used for submitting and reviewing reports, grantees must retain all records internally for a minimum of five years submission of the final expenditure report for compliance purposes.
Closeout Letter
Record Retention

## Slide 10
Frequently Asked Questions

## Slide 11
FAQs
Can program staff (i.e., digital navigators) continue to be funded during October-December?
    If you anticipate difficulty completing programmatic activities by this date, please contact your program/finance officers as soon as possible.
    Our team will support activities tied to existing documented commitments.
    No new programming may begin after Sept. 30.
Is the grant ending early?
    No. The period of performance runs through Dec. 31, 2026. The final quarter (October–December) is intended for closeout activities.
What if we have remaining funds after Sept. 30?
    Grantees should review their timeline, scope, and spending projections now to determine whether all awarded funds will be expended by the deadline. If you anticipate that funds will remain unspent, please contact your program and finance officers to discuss next steps, including potential award reduction.
    Any unspent funds (cash received but not used) or undrawn funds (awarded funds that were not requested) will be reconciled during the closeout process and returned as required.

## Slide 12
FAQs
Can devices/equipment continue to circulate through an organization after Sept. 30?
  Yes. Devices purchased during the period of performance may continue to be circulated as part of the organization's regular operations.
Can we charge internet or connectivity services (i.e., hotspots, wireless service, data usage) beyond Sept.30?
  Service costs may continue to be charged through the official award end date of Dec. 31, 2026.
Does my organization meet the single audit requirement?
  Any non-federal entity that expends $1 million or more in all federal awards (including funding from an NCDIT grant) during the entity's fiscal year must have a single audit conducted and submit a copy to our office.
  If your entity meets this threshold, please submit your most recently completed audit by the Jan. 8 reporting deadline.

## Slide 13
FAQs​
​What should the inventory equipment sheet during closeout reflect?
  At a minimum, the inventory sheet should include:
    Date of purchase
    Item description (e.g., laptop, tablet, hotspot)
    Model and serial number (if applicable)
    Quantity
    Distribution status
      If distributed, the date of distribution and anonymized recipient
What equipment should be tracked on our inventory sheet?
  Printers
  Cellphones
  Laptops
  Desktop computers
  Tablets
  Hotspots
  Servers or network equipment
  Vehicles/Trailers
  Smart screens
  Other
    If peripheral items (mice, headsets, laptop bags, etc.) are being distributed as a "device kit" you want to account for the full package

## Slide 14
FAQs​
Can we request all our funds to have in-house vs waiting?
  No, please continue to drawdown based on your quarterly projections. Ensure that you are drawing down enough funds to cover all your activities.

## Slide 15
Questions?